## Sheet1
Project Plan | Guangtong Shen, Jialiang Yu | 2016-10-03
MileStone | Tasks | Date | Guangtong | Jialiang | Question
Write Namenode in-memory meta data to a memory-mapped region via mmap in C | Write Array in Java to memory in malloc() in C | 2016-10-09 |  | √
| Contact Professor for mmap() API | 2016-10-12 |  | √
| Reading HDFS source find meta data data structure | 2016-10-12 | √
| Write meta data to mmap() address | 2016-10-17 | √ | √
| Compile HDFS code after change. Test | 2016-10-23 | √ | √
HDFS works on one node with meta data writing on NVMM after removing edit-log and fsimage | Reading HDFS source find edit-log and fsimage storage | 2016-10-28 | √ | √
| Remove edit-log and fsimage on primary node. | 2016-10-31 | √
| Remove editlog sync in secondary node. | 2016-10-31 |  | √
| Remove fsimage update and sync in secondary node. | 2016-11-06 |  | √
| Compile HDFS code after change. | 2016-11-13 | √ | √
| Test by reading and writing files to HDFS | 2016-11-20 | √ | √
One Namenode handle reading, the other handle writing | Sync memory-mapped region between two nodes. | 2016-11-27 | √
| Remove standby mode. Two node both in active mode. | 2016-11-27 |  | √
| Create load balancer between name nodes and clients | 2016-12-02 | √ | √ | How clients access name node originally?
| Route file change requests(meta data will change) to primary, file reading requests to secondary | 2016-12-04 | √ | √
| Compile HDFS code after change. (Two nodes are the same) | 2016-12-11 | √ | √
| Test by writing files and reading back to the load balancer. | 2016-12-16 | √ | √
The final step is of course having both namenodes handle both writes and reads |  | Spring 2017
Spring 2017
Spring 2017
Spring 2017
Spring 2017